## Intro
4th Year Software Test Plan
Project Name | Login Console
Project Manager | Naomi Hurley
Prepared by | Naomi Hurley and the 4th year Computing students
Tech Lead | To be confirmed
Date
Revision History
Revision | Author | Comment
1 | Naomi Hurley | Initial Draft

## Product No 1 or Sprint No 1
|  | Purpose: | To test the functionality of the developed application
LP (Linear Progression) |  |  |  | Visual Studio 2017 VS - Android Emulator
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
1 | 1 | TC.001 | Main Page | UI | 1. Launch App | Compiling | Main page is displayed | Main page is displayed | Pass
2 | 1 | TC.002 | Display Pages | UI | 1. Launch Application 2. Navigate to different pages | Compiling Navigation | Different pages should display | Different pages are displayed | Pass
3 | 1 | TC.003 | Display Workouts | Functionality | 1. Launch Application 2. Navigate to Main Page 3. Check for stored workouts | Storage | A list of workout should appear | Workouts appear | Pass
4 | 1 | TC.004 | Add Workout | Functionality | 1.Launch Application 2.Navigate to Main Page 3.Scroll down and click Add Workout Button | Navigation | Add workout page should appear | Add Workout page appears | Pass
4 | 1 | TC.005 | Add Workout | Functionality | 1.Launch Application 2.Navigate to Add Workout Page 3.Enter valid details 4.Save | Storage | Workout should be saved and page should be popped back to main page. | Workout is saved and page is popped back. | Pass
4 | 1 | TC.006 | Add Workout | Functionality | 1. Repeat Steps outlined int TC.005 | Storage | Workout should appear in list, it's day (e.g.: 1) being it's title and should increment for each workout present. | Does not increment | Fail | Defect No 1 Priority-2 Severity-Minor | To be fixed
5 | 1 | TC.007 | Navigation | Functionality | 1. Launch Application 2. Navigate to Help Page 3. Click the Squat button | Navigation. | Successful navigation to SquatWiki Page | SquatWiki page is displayed | Pass
5 | 1 | TC.008 | Navigation | Functionality | 1.Repeat steps in TC.007 for the rest of the available buttons on the page | Navigation. | Successful navigation to the relevant Wiki page. | Relevant Wiki page is displayed | Pass
6 | 1 | TC.007.1 | JSON | Database | 1. Restart the application 2.Navigate to main page 3.Check for previously stored workouts. | JSON storage. | Successfully load the list of previously stored workouts. | JSON not functioning, Workouts are not saved to a local database. | Fail | Defect No.2 Priority-1 Severity-Maximum | To be assigned

## Product No 2 or Sprint No 2
|  | Purpose: | This set of tests is intended to check main functionality developed
Test Run Title e.g. Login validation |  |  |  | Microsoft Internet Explorer 9 Windows 7 Microsoft Internet Explorer 10 Windows 7 Micresoft Internet Explorer 11 Windows 7 Microsoft Internet Explorer 8 Windows XP Microsoft Internet Explorer 7 Windows XP Firefox latest version Apple Safari Windows XP Apple Safari Google Chrome Windows XP Opera Windows XP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Results Pass/Fail | Bug # | Comments

## Test Progress
Tabs | Developped by | No of test cases | Tester | No of days | Browsers | Test cases passed | Test cases failed | To be done | Percentage done
Sprint No
Test Run description | Team A | 18 |  |  | All | 0 | 0 | 18 | 0%
Test Run description | Team B | 8 |  |  | N/A | 0 | 0 | 8 | 0%
Test Run description | Team C | 19 |  |  | All | 0 | 0 | 19 | 0%
Test Run description | Team D | 20 |  |  | All | 0 | 0 | 20 | 0%
Test Run description | Team C | 42 |  |  | All | 0 | 0 | 42 | 0%
Total |  | 107 |  |  |  |  | 0 | 0 | 0%